## FL TPFDL
STATE OF FLORIDA | [18 empty] | Date Revised:
State Emergency Response Team | [18 empty] | By: | G Van Treese, ESF 11
Unified Logistics Operations
Time Phased, Force and Deployment Data Listing (TPFDDL)
FOR OFFICIAL USE ONLY
PLANNING APPLIES TO THE FOLLOWING EVENTS
DISASTERS | [7 empty] | TERRORISM |  |  |  |  | INITIATION TIME | ACTION or RESOURCE | NIMS TYPING | PRIMARY ESF | ASSET | ACTION | TRIGGER | DTG
H | T | F | W | P | C | R | T | C | B | R | N | E | - / + HRS |  |  | SUPPORT AGENCY | CLASS | ID | POINT | COMPLETED
[13 empty] | -80 | Alert ESF 11 team members - Stand-by |  | ESF 11 | State | DACS | Activation | bar: DISASTERS H; DISASTERS F
[13 empty] | -72 | Activate core Team members to EOC |  | ESF 11 | State | DACS | Activation | bar: DISASTERS H
[13 empty] | -72 | Request food inventories from warehouses |  | ESF 11 | 1; State, vendor | DACS | Activation | bar: DISASTERS H; DISASTERS F
[13 empty] | -72 | Determine population affected/quantities needed (water & ice; commodities) |  | ESF 5; ESF 11 | 1; state, | FDEM, DACS | Activation | bar: DISASTERS H; DISASTERS F
[13 empty] | -72 | Identify pre-mobe area for delivery of water and ice |  | Logistics Section; DOF | State | FDEM, DACS | Activation | bar: DISASTERS H
[13 empty] | -72 | Contact vendors; determine availability of water and ice; ETAs for truckloads needed |  | ESF 11 | 1; vendors | DACS | Activation | bar: DISASTERS H; DISASTERS F
[13 empty] | -48 | GO/No Go on FPOs for water and ice. |  | ESF 11 | 1 | DACS | Anticipated point of landfall | bar: DISASTERS H
[13 empty] | -48 | Prepare Field POs |  | ESF 11 | 1 | DACS | bar: DISASTERS H
[13 empty] | -36 | Place orders-water and ice for delivery to designated pre-mobe location; establish # trucks expected per day |  | ESF 11 | 1; vendors | DACS | Anticipated point of landfall | bar: DISASTERS H; DISASTERS F
[13 empty] | -36 | Input food inventories into disaster inventory spreadsheet |  | BFD staff; ESF 11 | 1 | DACS | Activation | bar: DISASTERS H; DISASTERS F
[13 empty] | -36 | Determine anticipated food needs; if sufficient quantities of commodities in state warehouses |  | BFD staff; ESF 11 | 1; state | DACS | Activation | bar: DISASTERS H; DISASTERS F
[13 empty] | -24 | Contact other (local) vendors; determine local availability of water and ice; maximum quantities available per day |  | ESF 11 | 1; vendors | DACS | bar: DISASTERS H; DISASTERS F
[13 empty] | -24 | Alert ESF 11 LSA team members - Stand-by; information on possible LSA location(s), if known |  | Logistics Section; ESF 11 |  | DACS | bar: DISASTERS H
[13 empty] | -24 | Check/ready all LSA equipment, supplies, etc. |  | ESF 11 |  | DACS | bar: DISASTERS H
[13 empty] | -24 | Notify SFSAs-Authorize release of USDA commodities to disaster organizations for mass/congregate feeding |  | ESF 11; BFD staff | 1 | DACS | Evacuation; shelters opening | bar: DISASTERS H; DISASTERS F
[13 empty] | -24 | Notify USDA SERO - releasing commodities |  | ESF 11; BFD staff | 1 | DACS | Evacuation; shelters opening | bar: DISASTERS H; DISASTERS F
[13 empty] | -12 | Identify anticipated needs for baby formula/food |  | ESF 11; DOH/WIC staff | 1 | DACS | bar: DISASTERS H
[13 empty] | -12 | Contact baby food & formula vendors; determine prices, etc. |  | ESF 11 | 1; vendors | DACS | bar: DISASTERS H
[13 empty] | -12 | Determine availability of water tenders; contact dairies in FL as well as vendors |  | ESF 11; DOF | 1; state; vendors | DACS | bar: DISASTERS H
[13 empty] | -12 | Prepare ARF for water tenders, if needed. Include in request: drivers, tractor to deliver to location where needed, filling, maintenance, etc. |  | ESF 11 | 1 | DACS | bar: DISASTERS H
[13 empty] | E | Identify water & ice truckloads arrived at pre-mobe area |  | ESF 11; Pre-mobe area staff | 1 | DACS | bar: DISASTERS H
[13 empty] | E | Identify PODs; determine destination for each truck at pre-mobe |  | Logistics Section; DOF | 1 |  | Landfall | bar: DISASTERS H
[13 empty] | E + 12 | Dispatch trucks to designated PODs; provide address, coordinates to ea. truck |  | Logistics Section; DOF; ESF 11 | 1 |  | Winds dying; roads open | bar: DISASTERS H
[13 empty] | 12 | Based on severity of event, determine anticipated quantities of water and ice needed daily |  | ESF 11 | 1 | DACS | Impact of storm; demand | bar: DISASTERS H
[13 empty] | 12 | Place orders for additional loads of water and ice for delivery to LSA(s) as needed |  | ESF 11 | 1; vendors | DACS | Impact of storm; demand | bar: DISASTERS H; DISASTERS F
[13 empty] | 12 | Submit ARF for baby food/formula/diapers, etc. if needed |  | ESF 11 | vendors | DACS | Impact of storm; demand | bar: DISASTERS H
[13 empty] | 12 | Work with Salvation Army, Red Cross, etc. regarding anticipated food needs for feeding operations |  | ESF 11 | 1 |  | Impact of storm; demand | bar: DISASTERS H; DISASTERS F
[13 empty] | 12 | Place order for baby food/formula from vendor, if needed |  | ESF 11 | 1; vendors | DACS | Impact of storm; demand | bar: DISASTERS H
[13 empty] | 18 | Make arrangements/reserve accommodations for LSA team members |  | BFD; ESF 11 | vendors | DACS | bar: DISASTERS H
[13 empty] | 18 | Deploy LSA team(s) as needed |  | ESF 11 | 1 | DACS | Impact of storm; demand | bar: DISASTERS H
[13 empty] | 24 | Monitor arrivals of water and ice trucks |  | ESF 11 | 1 | DACS | Extent of event; demand | bar: DISASTERS H; DISASTERS F
[13 empty] | 48 | Monitor water and ice usage; increase or decrease order as needed or submit ARF to FEMA for Army Corps of Engineers assistance |  | ESF 11; Logistics Section | 1 | DACS | Extent of event; demand | bar: DISASTERS H; DISASTERS F
[13 empty] | 48 | Monitor food inventories at warehouse |  | ESF 11; BFD | 1 | DACS | Extent of event; demand | bar: DISASTERS H; DISASTERS F
[13 empty] | 72 | Submit ARF for USDA as additional commodities needed |  | ESF 11 |  | DACS | Extent of event; demand | bar: DISASTERS H; DISASTERS F
[13 empty] | 90 | Monitor availability of water, ice, baby supplies |  | ESF 11 |  | DACS | Extent of event; demand | bar: DISASTERS H; DISASTERS F
[13 empty] | As needed | Transition LSA team members after designated # of days in the field |  | ESF 11 |  | DACS | Extent of event; demand | bar: DISASTERS T
[13 empty] | end | Recover resources; return to their source(s) |  | ESF 11 |  | DACS | End of response mode | bar: DISASTERS H
[13 empty] | within 30 days of end | Gather information RE: commodities; submit reports to USDA |  | ESF 11 |  | DACS | End of response mode | bar: DISASTERS T
Note on Q11: FDEM Logistics Section:
Note on R11: FDEM Logistics Section: 1: Substuance 2. Consumable Expandables 3. Fuels, Bulk 4. Building Materials 5. Government Services 6. MWR 7. Non- Expendable Property 8. Medical 9. Repair / Maint. Contracts 10. Contracted Services
Note on Q12: FDEM Logistics Section:
Note on Q13: FDEM Logistics Section:
Note on Q14: FDEM Logistics Section:
Note on Q16: FDEM Logistics Section:
Note on Q17: FDEM Logistics Section:
Note on Q18: FDEM Logistics Section:
Note on Q20: FDEM Logistics Section:
Note on Q21: FDEM Logistics Section: